Debe ser un valor entero mayor de 0
El valor debe ser una fecha
Duración mínima 3, máxima 24 (días laborables)
## Config
Proyect
Custom software projects dashboard

Sprint Number	Start date	Days	Working days
1	42534	4	4

TASKS		TEAM	BANK HOLIDAYS
TYPES	STATUS
Analysis	Pending	Student1
Design	In progress	Student2
Code	Finished	Student3
Test	Removed	Student4

## Data
		SPRINT	START	DURATION
		1	13/06/16	4			L	M	X	J	V	S	D
							13/06/16	14/06/16	15/06/16	16/06/16	17/06/16	18/06/16	19/06/16
				Remaining Tasks				5	3	0	0	0	0					Analysis	Pending	Student1
				Remaining working hours			18	11	5	0	0	0	0					Design	In progress	Student2
SPRINT BACKLOG							EFFORT					Code	Finished	Student3
Backlog ID	Task			Type	Status	Responsible					Test	Removed	Student4
	Make 2 boards with threeboard			Code	Pending		4	1	0					0	0	0
	Make demo elasticSearch + Kibana			Code	Pending		4	0	0					0	0	0
	Install Kibana development			Design	Pending		4	4	0					0	0	0
	Add a new panel in Kibana			Code	Pending		2	2	2					0	0	0
	“Hello World” with Kibana plugin			Code	Pending		2	2	1					0	0	0
	Simple elastiSearch query and pie plot			Code	Pending		2	2	2					0	0	0
									0	0	0

## Graphs
	Project					SPRINT		START		DAYS
	Name of the project					1		42534		4

Effot Graphic / sub-title / Remaining working hours

Tasks Graphic / sub-title / Remaining Taks

Members Graphic / sub-title / Remaining Working Hours

	42534	42535	42536	42537	42538	42539	42540	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509
Student1	0	0	0	0	0	0	0	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509
Student2	0	0	0	0	0	0	0	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509
Student3	0	0	0	0	0	0	0	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509
Student4	0	0	0	0	0	0	0	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509
0	0	0	0	0	0	0	0	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509	Err:509